## Sheet1
Task Number | Feature Name | Category | Priority | Story Points | Notional Points total = 100 1pt = 30min | Start | Finish | Duration | Status | Comments
Theme | Ship Movement
Epic 1 | Player Controller | Player Agency |  | 9 | 8
Task 1 | 3 axis force application |  | High | 2 | 2 | 03/05/2024 | 03/05/2024 | 1 | Complete
Task 2 | Yaw Application |  | High | 2 | 1 | 03/05/2024 | 03/05/2024 | 0.5 | Complete
Task 3 | Camera follow |  | Low | 3 | 2 | 03/05/2024 | 04/05/2024 | 1 | Complete
Task 4 | Optimize controls |  | Medium | 2 | 3 | 04/05/2024 | 05/05/2024 | 1 | Needs Playtesting
Epic 2 | World physics |  |  | 6 | 5
Task 1 | Celestial body attraction | Physics | High | 5 | 4 | 01/05/2024 | 01/05/2024 | 2 | Complete
Task 2 | Universal settings | System parameters | Low | 1 | 1 | 01/05/2024 | 01/05/2025 | 1 | Complete
Theme 2 | Player Feedback |  |  | 24 | 25
Task 1 | Orbital path visualizer | Movement assistance | High | 8 | 7 | 04/05/2024 | 05/05/2024 | 3 | Complete
Task 2 | Compass | nav assistance | Low | 1 | 1 | 05/05/2024 | 05/05/2024 | 0.5 | Complete | Removed from game
Task 3 | Velocity indicator | Movement assistance | Medium | 1 | 1 | 05/05/2024 | 05/05/2024 | 0.5 | Complete
Task 4 | Particle FX | Movement assistance | Low | 2 | 3 | 05/05/2024 | 30/05/2024 | 3 | Complete
Task 5 | Thrust indicator | Movement assistance | Medium | 1 | 2 | 06/05/2024 | 06/05/2024 | 1 | Complete
Task 6 | Ghost of previous attempt | Race feedback | Low | 5 | 6 | 23/05/2024 | 26/05/2024 |  | Incomplete
Task 7 | Haptic feedback | Movement assistance | Low | 1 | 1 | 18/05/2024 | 19/05/2024 |  | Incomplete
Task 8 | Implement Sounds | General Feedback | Low | 2 | 1 | 29/05/2024 | 30/05/2024 |  | Incomplete | Waiting for assets
Task 9 | Distance indicator | nav assistance | Medium | 3 | 3 | 15/05/2024 | 16/05/2024 |  | Incomplete
Theme 3 | World Elements |  |  | 16 | 10
Task 1 | Static Planets | Static Celestials | High | 2 | 1 | 01/05/2024 | 01/05/2024 | 1 | Complete
Task 2 | Asteroid Belts | Moving Obstacles | Medium | 5 | 3 | 14/05/2024 | 15/05/2024 |  | Incomplete
Task 3 | Moons | Moving Obstacles | Medium | 2 | 1 | 14/05/2024 | 15/05/2024 |  | WIP
Task 4 | Checkpoints | Waypoints | High | 2 | 3 | 13/05/2024 | 13/05/2024 |  | WIP
Task 5 | Track path hints | nav assistance | High | 5 | 2 | 16/05/2024 | 17/05/2024 |  | Complete
Theme 4 | Track Design |  |  | 28 | 17
Task 0 | Test track | Testing | High | 2 | 1 | 02/05/2024 | 02/05/2024 | 1 | Complete
Task 1 | Design 5 tracks | Track Design | Medium | 13 | 8 | 16/05/2024 | 21/05/2024 |  | WIP | 1/5
Task 2 | track boundary implementation | Track Design | Low | 2 | 1 | 16/05/2024 | 21/05/2024 |  | Incomplete
Task 3 | Track Path Visualisation | nav assistance | High | 3 | 2 | 16/05/2024 | 17/05/2024 | 2 | Complete
Task 4 | Determine track goals | Track Design | Low | 8 | 5 | 20/05/2024 | 21/05/2024 |  | Incomplete
Task 5 | Tutorial Design | Tutorial | High | 5 | 4 | 25/05/2024 | 26/05/2024 |  | Incomplete
Theme 5 | Race Logic |  |  | 16 | 12
Task 1 | Race Timer | Game System | Medium | 5 | 3 | 16/05/2024 | 21/05/2024 |  | WIP
Task 2 | Track Selector | Game System | Low | 1 | 1 | 20/05/2024 | 21/05/2024 |  | Incomplete
Task 3 | Track Leaderboard saves | Game System | Low | 3 | 2 | 23/05/2024 | 25/05/2024 |  | Incomplete
Task 4 | Checkpoints | Track Design | Medium | 2 | 2 | 16/05/2024 | 21/05/2024 |  | WIP
Task 5 | Record ghost time | Race feedback | Medium | 5 | 4 | 23/05/2024 | 25/05/2024 |  | Incomplete
Theme 6 | UI Screens |  |  | 11 | 9
Task 1 | Track Selector | General UI | Low | 1 | 2 | 17/05/2024 | 21/05/2024 |  | Incomplete
Task 2 | Pause Screen | General UI | Medium | 1 | 1 | 06/05/2024 | 21/05/2024 |  | WIP | Functional
Task 3 | Leaderboard | General UI | Low | 3 | 2 | 23/05/2024 | 25/05/2024 |  | Incomplete
Task 4 | Race Finished | Game System | Low | 1 | 1 | 20/05/2024 | 21/05/2024 |  | Incomplete
Task 5 | Game HUD | Game System | High | 5 | 3 | 05/05/2024 | 21/05/2024 |  | WIP | Functional
Theme 7 | Art |  |  | 29 | 14
Task 1 | Sounds | General Feedback | Low | 8 | 4 | 27/05/2024 | 29/05/2024 |  | Incomplete
Task 2 | Ship Model | General UI | Medium | 13 | 6 | 27/05/2024 | 30/05/2024 | 0.5 | Complete
Task 3 | Ship Particles | General Feedback | Low | 3 | 1 | 30/05/2024 | 30/05/2024 | 3 | Complete
Task 4 | Style Guide | General UI | Medium | 5 | 3 | 24/05/2024 | 26/05/2024 |  | Incomplete
Backlog